## ReadMe
EINSTEIN Tool Version Control

V	Versions

V005	HS		Integration of list “bugs and ideas”
V008	HS		Some new bugs/ideas added
V009		13/04/08	New comments introduced for panel/module HP, panelEA, ...
V010	HS		Some new bugs/ideas added

## BugsNIdeas
EINSTEIN Tool: List of bugs and ideas to be incorporated

Entry date	Bug advise/idea from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
Scroll-up menu
03/03/08		DB edit option	Names of DB should be adapted to specifications	high	V0.0	03/03/08	HH	pending
07/04/08	HS	view alternatives	Alternatives – view should be activated	high	V0.0	pending		pending
21/04/08	HS	project open/new	Menu bar should lead to PanelQ0	high	V0.0	21/04/08	TS	pending

Tree
06/03/08		SEC	SEC by product / unit operation should adapt to the products / unit operations specified in the given industry	high	V0.0	pending		pending

GUI – general
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high	V0.0	13/04/08	TS	pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	high	V0.0	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high	V0.0	18/04/08	SD	pending
18/04/08	TS	UTF-8 recommended	Windows usa algo parecido a / ISO-8859-1 (llamado también Latin-1). Esta codificación basta para los / idiomas 'occidentales' como castellano, catalán, alemán, francés, / inglés. Pero los idiomas eslavos usan otras (ISO-8859-2, etc.) y si esta / herramienta se quiere usar a nivel de toda Europa, sería mejor pasarse a / UTF-8. El problema radica en que necesitas tener un editor de texto que lo / acepte. / De momento, como sólo estamos usando texto inglés, no habría que hacer / nada especial, excepto recrear la base de datos pasándola a UTF-8 y usando / una versión de Python que acepte UTF-8 también. Creo que siempre hay dos / versiones de Python, una sólo para inglés y Latin-1 y otra / internacionalizada para UTF-8.	low	V1.0	pending		pending

DB Editor
03/03/08		Exit button	No exit button is foreseen	normal	V0.0	03/03/08	HH	pending
25/02/08		Pulldown menu in DB Benchmark	Up to now data bases that are linked with each other have to be entered by the ID-value. No pull-down menu is foreseen. This should be changed later on	normal	V1.0	pending	-	pending
02/04/08		diferentes Dbs	possibility to edit different equipment DB's: heat pump, boiler, / additional DB's that will come in the future (CHP, chillers, solar / thermal, ...) [por ahora abre la tabla UHeatPump, la cual es la / tabla equivocada]	high	V0.0	02/04/08	TS	pending
02/04/08		button OK/Cancel		high	V0.0	02/04/08	TS	pending
02/04/08		select by double clicking		high	V0.0	02/04/08	TS	pending
13/04/08	HS	DB Editor	preselected list of equipment should be possible	high	V0.0	13/04/08	SD	pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high	V0.0	pending	-	pending
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	high	V0.0	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.0	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V0.1	pending	-	pending

energyStatistics
02/04/08	HS	window overlap	Switching between windows EA/EM/EH the hide() is not activated.	high	V0.0	02/04/08	TS	pending
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high	V0.0	02/04/08	TS	pending
02/04/08	HS	units in display	should be possible to display data in different units; / units should be eliminated from legend	high	V0.0	02/04/08	TS	pending
02/04/08	HS	scroll bars in tables	try to avoid	high	V0.0	02/04/08	TS	pending
02/04/08	HS	layout windows	tables should have the same width as figures, ....	high	V0.0	02/04/08	TS	pending
07/04/08	HS	EA windows	number of digits and thousands separtator	normal	V0.0	07/04/08	TS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal	V0.0	07/04/08	TS	pending
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal	V0.0	pending	-	pending
07/04/08	HS	CO2 + nuclear	inlcude CO2 and radioactive waste in the same screen	normal	V0.0	pending	-	pending
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high	V0.0	13/04/08	SD	pending

E-Questionnaire
21/11/07	CV	Quick assessment	concerning the "one page-simplified -summary questionnaire" that we mentioned on skype last time, I was wondering if this same simplified interface can be also used later on for the (quick) self-assessment module to be used by distance. / Of course I am not able now to see how the self-assessment is going to be mplemented and if it will be based on the same amount of info required for the core tool...It is just a "small window" to be taken open if when implementing the questionnaire and developing the tool in order to save time later on.	normal	V1.0	pending	-	pending
06/03/08		graphical window-layout	Graphical layout into the design of the windows	normal	V0.1	18/04/08	TS	pending
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	normal	V0.1	pending	-	pending
02/04/08	HS	version for modules	possibility to call from modules; block add/delete; add OK+cancel	high	V0.0	02/04/08	TS	pending
07/04/08	HS	Lists	predefined text for lists (EquipeType, UnitOp, etc.)	normal	V0.0	pending	-	pending

SQL
10/03/08	TS	Capital letters in VarNames	DB is referred to in lowercase letters: in windows works, but linux not !!!	normal	V0.0	pending	-	pending
07/04/08	HS	Benchmark DB	Include Benchmark DB in SQL	high	V0.0	07/04/08	SD	pending
18/04/08	SD	queries	queries with [0] at the end give error in empty lists / subsitute by query of list and then assignment of index	high	V0.0	18/04/08	all	pending

Questionnaire
10/03/08	CV	FuelConsum	better explanatory text	normal	V0.0	pending	-	pending

Self-learning and DB Update
21/11/07	CV	Self-learning of tool	Do you think that it would be useful and to feasible to foresee an authomatic update of the databases / and a statistics module where results of an audit campaign can be stored and compared, summarised etc., by industry sector, country etc.? / Or this module/task should be something completely stand-alone? / We should produce an evaluation report of the audit campaign...	low	V1.0	pending	-	pending

heatPump
07/04/08	HS	Lists	panel peta si lista equipos (HP's) es vacía ...	normal	V0.0	07/04/08	SD	pending
07/04/08	HS	panel	Pre-assignment in choice; lower-right data as read-only (Static text) ?	normal	V0.0	07/04/08	TS	pending
13/04/08	HS	Module-DeleteEq	DB.commit to be activated ???	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	selected rows should appear in dark	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	after deleting an equipment, the rows continue appearing in blue. Should be white again	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	editing an equipment by mouse-double click (Q4 – panel appears), the values are not changed after leaving Q4.	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	calculateCascade to be activated after adding/deleting/changing equipment	high	V0.0	pending		pending
13/04/08	HS	moduleHP	Well-working of design-assistant has to be checked	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	function deleteEquipment for erasing space from addEquipmentDummy	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	default buttons should be fully operative	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	adaptation of graphics to specifications	high	V0.0	13/04/08	SD	pending

## FileStructure
EINSTEIN Tool – file structure

Folder					Files	Description	Developed by	Version	Date
einstein
	GUI
					einstein.py	main file	HH
					gui_Q1.py	page1 of the questionnaire
					(...)
					gui_heatPump.py	interactive window for heat pump
	modules
		boiler				boiler.py
		energyStatistics				estat.py
		heatPump				heatPump.py

	auxiliary
					calc.py

	sql
					einsteinDB.txt	???
					einsteinDB.sql	???

## Functions
	EINSTEIN Tool – functions and classes

	Functions:
						Files	Member of class	Description	Inputs	Outputs	Developed by	Version	Date
Calculation Modules	fictGUI					fictGUI.py					SD	v001	07/01/08
Consistency check		consistencyCheck					ccheck.py					CV

Energy statistics		energyStatistics					estat.py					SD	v001	07/01/08
			calcEnergyIntensity				calc.py					SD	v001	07/01/08

Heat Recovery Module		heatRecovery

		hcSupply
HeatPump Module (HPM)			selectHeatPump(sql,DB,Qid,Aid,PSid,LEVEL)				heatpump.py		Function of the HPM that selects appropriate heat pumps from the DBHeatPump on the basis of the given heat demand (QD) and heat availability (QA) curves allocated in the tables EnergyFlowsQ... of the mySQL database. / As a result returns a list of heat pump IDs according to DBHeatPump.	sql - MySQL connector / DB - einstein database / Qid - Questionnaure_id / Aid - Alternative Proposal ID / PSid - PSetUpData_ID / LEVEL - level of user interaction (1,2,3)	List of DBHeatPump_IDs	SD	v001	06/02/08
			heatPumpRecalc(sql,DB,Qid,Aid,HPid)				heatpump.py		Function of the HPM that calculates the Heating capacity, absorbed energy and COP of a selected heat pump (by ID) on the basis of the given heat demand (QD) and heat availability (QA) curves allocated in the tables EnergyFlowsQ... of the mySQL database.	sql - MySQL connector / DB - einstein database / Qid - Questionnaire_id / Aid - Alternative Proposal ID / LEVEL - level of user interaction (1,2,3)	dotQh - heating capacity / dotQc - cooling capacity / dotQw - consumed power / COPh_i - hourly COP / COPh - annual COP / Fpl_i - part load factor for each hour / Fpla - annual part load factor == to annual operation hours	SD		06/02/08
			userDefinedLevel1(sql,DB,Qid,Aid)				userdefined.py		Function for charging the user-defined data for HP selection from einsteinDB when LEVEL=1	sql - MySQL connector / DB - einstein database / Qid - Questionnaire_id / Aid - Alternative Proposal ID				06/02/08
			userDefinedLevel2(sql,DB,Qid,Aid,PSid)				userdefined.py		Function for charging the user-defined data for HP selection from einsteinDB when LEVEL=2	sql - MySQL connector / DB - einstein database / Qid - Questionnaure_id / Aid - Alternative Proposal ID / PSid - PSetUpData_ID				06/02/08
			userDefinedLevel3(sql,DB,PSid)				userdefined.py		Function for charging the user-defined data for HP selection from einsteinDB when LEVEL=3	sql - MySQL connector / DB - einstein database / PSid - PSetUpData_ID				06/02/08
			inputData(sql,DB,Qid,Aid,PSid,HPTypeUD)				heatpump_input.py			sql - MySQL connector / DB - einstein database / Qid - Questionnaure_id / Aid - Alternative Proposal ID / PSid - PSetUpData_ID / HPTypeUD - heat pump type userdefined				06/02/08
			chargeCurvesQDQA(sql,DB,Qid,Aid)				heatpump_input.py			sql - MySQL connector / DB - einstein database / Qid - Questionnaure_id / Aid - Alternative Proposal ID				06/02/08
			selectHeatPumpFromDB(dotQ,listDB)				auxiliary.py			dotQ - reference capacity / listDB - list of ascending capacities				06/02/08
			last_filled(list)				auxiliary.py			list - list of doubles				06/02/08
			first_filled(list)				auxiliary.py			list - list of doubles				06/02/08
			indx(val)				auxiliary.py		returns the index of the temperature vector(list) when given the value (T = range(0,405,5))	val - value of list member	returns index of T			06/02/08
			val(indx)				auxiliary.py		returns the temperature value when given the index of the vector(list)	indx - index of a list	returns value of T			06/02/08
			findQfromT(T,listQ)				auxiliary.py		Returns the energy value from the energy vector(list) corresponding to the temperature T making linear interpolation	listQ - energy values list	returns value of Q			06/02/08
			findTfromDemandCurve(Q,listQ,listT)				auxiliary.py		Returns temperature for the corresponding value of Q in the listQ (Heat Demand curve). Note: works only with strictly ascending listQ curves (accumulated)! / If does not find correspondance in the T interval, returns T = 0.0	Q - reference value / listQ - energy values list (ascending), QD / listT - temperatures list	corresponding T value			06/02/08
			findTfromAvailabCurve(Q,listQ,listT)				auxiliary.py		Returns temperature for the corresponding value of Q in the listQ (Heat Availability curve). Note: works only with strictly descending listQ curves (accumulated)! / If does not find correspondance in the T interval, returns T = 0.0	Q - reference value / listQ - energy values list (descending), QA / listT - temperatures list	corresponding T value			06/02/08
			calculateCOPth(HPTypeUD,Th_i,Tc_i,TgeUD)				auxiliary.py		Calculates theoretical (Carnot) COP	HPTypeUD - heat pump type userdefined / Th_i - condensing temperature for i-th hour / Tc_i - evaporating temperature for i-th hour / TgeUD - userdefined T generation (abs. only)	Theoretic COP i-th hour			06/02/08
			calculateCOP(HPTypeUD,COPht_i,copexListDB,j)				auxiliary.py		Calculates real COP = COPex.COPth	HPTypeUD - heat pump type userdefined / COPht_i - theoretic COP i-th hour / copexListDB -ordered list of exergetic COPs from database	Real COP i-th hour			06/02/08
Boiler&Burner	initModule					ModuleBB.py	ModuleBB	Carries out all the initialisation of the boiler module.			HS	V0.01	11/03/08
	exitModule					ModuleBB.py	ModuleBB	Carries out all the actions necessary before leaving the module			HS	V0.01	11/03/08
	storeModulePars					ModuleBB.py	ModuleBB	Saves the parameters of the module (design assistant options, ...)			HS	V0.01	11/03/08
	delete					ModuleBB.py	ModuleBB	deletes a boiler in the active alternative	BBid: identifier of the boiler	BBList: updated list of equipments	HS	V0.01	11/03/08
	add					ModuleBB.py	ModuleBB	adds a boiler in the active alternative	BBid: identifier of the boiler	BBList: updated list of equipments	HS	V0.01	11/03/08
	retrieveDeleted					ModuleBB.py	ModuleBB	retreives boilers that have been deleted previously		RetreivalList: list of equipment that can be retreived	HS	V0.01	11/03/08
	designAssitant1					ModuleBB.py	ModuleBB	carries out step 1 of design assitant from button “run desing assistant” until first user interaction.		BBList: updated list of equipments	HS	V0.01	11/03/08
	designAssitant2					ModuleBB.py	ModuleBB	carries out step 2 of design assitant after first user interaction.		BBList: updated list of equipments	HS	V0.01	11/03/08
	calculateEnergyFlows					ModuleBB.py	ModuleBB	Calculates the contribution of the current boiler to the energy supply	BBid: identifier of the boiler	QDmod,QAmod: updated heat demand after boiler use / QEq: Contribution of equipment to total heat supply / t_op: nominal annual operating hours / f_pl: part load factor	HS	V0.01	11/03/08
	calculateCascade					ModuleBB.py	ModuleBB	Calculates the full cascade of boilers following the priority list		QDmod,QAmod: updated heat demand after boiler use / QEq: Contribution of equipment to total heat supply / t_op: nominal annual operating hours / f_pl: part load factor	HS	V0.01	11/03/08
		pSQL					pSQL.py					HH		07/01/08
			various				mxdatetime.py					---		07/01/08
			various				datetime.py					---		07/01/08

	Class definitions:
Boiler&Burner	ModuleBB					ModuleBB.py		Class containing all data and methods of the boiler module
Heat Pump	ModuleHP					ModuleHP.py		Class containing all data and methods of the heat pump module

	Auxiliary tools:
	einstein					einstein.py					SD	v001	07/01/08