## Versions
EINSTEIN Tool: Planing of versions

V1.0	15/10/08	Base version for training courses / Should be 90 % operative
V1.0.03	30/11/08	Base version for EINSTEIN audit campaign / Correction of most serious bugs detected
V1.0.04	31/03/09	CIMNE contribution to EINSTEIN / (spanish national project)
V1.1	Mid 2009	End of EINSTEIN project
V1.2	End 2009 ?	Additional add-ons from national projects

V2.0	???	In the future when everything is better ...

## BuggyBugs
EINSTEIN Tool: List of buggy bugs

Entry date	To do from	Topic	Description	Priority	Effort	To be changed until version	Notification date	Responsible	Status
Scroll-up menu
03/03/08		DB edit option	Names of DB should be adapted to specifications			V0.0	03/03/08	HH	ok
07/04/08	HS	view alternatives	Alternatives – view should be activated; -> to be revised	high		V0.1	30/04/08	TS	pending
21/04/08	HS	project open/new	Menu bar should lead to PanelQ0	high		V0.0	21/04/08	TS	ok
14/07/08	HS	General	Display of alternative / project ... does not update if new alternatives / are created -> vinculate with SetActiveAlternative/Project	high		V1.0b	pending	HS	fixed

Tree
06/03/08		SEC	SEC by product / unit operation should adapt to the products / unit operations specified in the given industry	high		V1.0a	pending		pending
23/06/08	HS	General	Eliminate tree-items not used	high		V1.0b	pending

GUI – general
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high		V1.0a	13/04/08	TS	pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	normal		V1.0a	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high		V0.0	18/04/08	SD	ok
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high		V0.1	13/04/08	TS	pending
18/04/08	TS	UTF-8 recommended	Windows usa algo parecido a / ISO-8859-1 (llamado también Latin-1). Esta codificación basta para los / idiomas 'occidentales' como castellano, catalán, alemán, francés, / inglés. Pero los idiomas eslavos usan otras (ISO-8859-2, etc.) y si esta / herramienta se quiere usar a nivel de toda Europa, sería mejor pasarse a / UTF-8. El problema radica en que necesitas tener un editor de texto que lo / acepte. / De momento, como sólo estamos usando texto inglés, no habría que hacer / nada especial, excepto recrear la base de datos pasándola a UTF-8 y usando / una versión de Python que acepte UTF-8 también. Creo que siempre hay dos / versiones de Python, una sólo para inglés y Latin-1 y otra / internacionalizada para UTF-8.	high		V1.00	pending		solved
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	high		V1.00	17/04/08	HS	solved
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high		V0.0	18/04/08	SD	ok
16/09/08	HS	Displayclasses	Unit Fraction 100% converts to 100, not to 1.0 / Distribution heat and cold: / insulation: 0.01m can not be entered - programm jumps to 0.1m! in mm it is correct....10mm = 0.1m??	high	low	V1.1	pending
20/04/09	HS	GUI Tables	Error occurs in data passing via SetGraphicsData, when numpy-array is used. Mixed data formats are unified to something (the first ?), e.g. double to strings ... ; problems arise with numbers such as 2.27 e-13 which in numpy conversion to string are converted into u”2.27” / -> unify whether number of digits is defined in GUI or in the modules / (at the moment only change in PanelEA4b, where number of digits is defined in the module).	high	medium	V1.1	pending
28/10/08	SD	delete project	Since update 278 delete project not working on some computers	high	?	V1.1	pending
23/09/08	HS	IntEntry	PanelQ4 (year of manufacturing, number of equipes -> does not store / display). Temporarily substituted by float entry with decimals = 0	normal	low	V1.1	pending
23/09/08	HS	displayclasses	min/max value should be related to internal Value, not to display value	normal	low	V1.1	pending
17/10/08	CV	settings	Settings: debugging mode does not memorise the opcion selected	normal	low	V1.1	pending
25/09/08	HS	auditor db	at present no way to enter auditor contact information ...	normal	medium	V1.1	pending
19/01/09	HS	<<< >>> buttons	systematic check of <<< OK Cancel >>> options necessary	low	low	V1.1	pending

Translations
19/01/09	HS	_U() functions and gettext	the _U() functions probably block the possibility to extract translatable text from the source code ... -> 2B checked	high	low	V1.1	pending
19/01/09	HS	Latin-2	Systematic checking of Einstein for Latin-2 users	high	low	V1.1	pending
19/01/09	HS	save language setting	Language setting cannot be saved	normal		V1.1	pending

Graphics
26/06/08	HS	refresh	Problem with refresh of graphics. Tom has some idea -> to be implemented	high		V1.01	26/06/08	TS/HS	pending
31/10/08	BS	graphics	- Check that all diagramms are really functioning at the first time and / that the axes are visible - Flo already told me that it is hard in / Python, but we got the feedback that this has high prioirity. Also to / check which diagramms are not working (e.g. in panel alternative / proposals) and either delete them for now or improve them.

DB Editor
03/03/08		Exit button	No exit button is foreseen	high		V1.0a	pending	-	pending
25/02/08		Pulldown menu in DB Benchmark	Up to now data bases that are linked with each other have to be entered by the ID-value. No pull-down menu is foreseen. This should be changed later on	high		V1.01	28/06/08	TS	pending
02/04/08		diferentes Dbs	possibility to edit different equipment DB's: heat pump, boiler, / additional DB's that will come in the future (CHP, chillers, solar / thermal, ...) [por ahora abre la tabla UHeatPump, la cual es la / tabla equivocada]	high		V1.0a	02/04/08	TS	pending
02/04/08		button OK/Cancel		high		V1.0a	02/04/08	TS	pending
02/04/08		select by double clicking		high		V1.0a	02/04/08	TS	pending
13/04/08	HS	DB Editor	preselected list of equipment should be possible	high		V1.0a	13/04/2008 / again: / 28/06/2008	SD / SD	ok
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	high		V1.1	19/06/08	TS	pending
29/06/08	HS	DB Content	Nulls or other corrupt content in DB's may give problems / -> security feature should be foreseen ... / (example: HP Module with None in HPHeatCap	high		V1.0a	pending		generic problem

File I/O (export/import project)
23/06/08	HS	import/export	links to be copied	high		V1.0a	23/06/08	TS	fixed (HS)
16/09/08	HS	import/export	import gives Problems, if previously the project with the highest ID has been deleted ... (conflict of auto-increment in the questionnaire table, and look-up of the import function) / has been provisionnally fixed adding always a dummy project. / Better solution should be found for saving ID'No's	low		V1.1	16/09/08	HS	provisional fix (Sept.08)

SQL
10/03/08	TS	Capital letters in VarNames	DB is referred to in lowercase letters: in windows works, but linux not !!! check if now it's ok	low		V1.1	pending	-	pending
18/04/08	SD	queries	queries with [0] at the end give error in empty lists / subsitute by query of list and then assignment of index	normal		V1.0a	18/04/08	all	controlled
14/07/08	HS	backup	ERROR MySQL binary folder not known	normal		V1.0b	14/07/08	TS	fixed
16/10/08	HS	Database	Several Bugs in SQL tables detected: text declared as “DOUBLE” etc. / -> revise everything, especially the early definitions (first updates)	low		V1.1	pending	-	pending

Paper Questionnaire

E-Questionnaire
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	high		V1.0b	pending	-	pending
25/04/08	HS	Q4	Delete in Q4 doesn't work. / Equipe type – is not passed correctly to addHP, ...	high		V0.1	25/04/08	HS	pending
12/06/08	HS	Q1...Q9	Reasonable limits for value entries ...	high		V1.01	12/06/08	SD	pending
23/06/08	HS	Q1...Q9	Automatic translation from volume-flow to mass-flow	high		V1.00	pending
23/06/08	HS	Q1...Q9	height of numCtrl entry fields -> adjust to unit-selector	high		V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	Rounding errors in numCtrls	high		V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	NumCtrls = None	high		V1.0a	June 08	SD	pending
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	high		V1.00	pending	-	pending
12/06/08	HS	Q1	Link choices for NACE and product codes	high		V1.0a	12/06/08	SD	pending
12/06/08	HS	Q1	Link text entry branch / sub-branch with nace-codes	normal		V1.0	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: while no defintive solution: improve the comments in the tool tips	normal		V1.01	pending		pending
19/01/09	HS	min/max in GUI	revise minimum / maximum values in GUI; reference to INTERNAL units and not to Display units !!!	normal			pending		pending
19/01/09	HS	Processes with name = None	can not be eliminated any more	normal			pending		pending
07/11/09	TC Madrid	simplified Q	simplified Q with reduced amount of data would be nice ...	normal	medium	?	pending		pending

PanelQ1
19/06/08	HS	Q1	Entering from PanelQ0 by “open project”: error messages appear trying to open Q1	high		V1.0a	19/06/08	TS	pending
	JOINTS	Q1	branch and sub-branch: not possible to insert a description when click on OK it gives back NONe	normal		V1.0.03ff	pending		pending
PanelQ2
12/06/08	HS	Q2	Layout	high		V1.0a	11/06/08	TS	pending
PanelQ3
12/06/08	HS	Q3	Reasonable limits; define missing units	high		V1.0a	12/06/08	SD	ok
16/06/08	HS	Q3	Layout; numctrls = None; activate unit conversion	high		V1.0a	16/06/08	TS	pending
23/06/08	HS	Q1...Q9	with of description field	normal		V1.01	June 08	SD	pending
	CV	Q3	Process questionnaire: / change in panelQ3 and also in list of parameters the folloing definitions: / Inlet temperature of process medium (before internal heat recovery) / Inlet temperature of process medium (after internal heat recovery) / title: Internal and external waste heat recovery for the process / In the box at least the position and move up the inlet temperature	normal		V1.0.03ff
	CV	Q3 piping	Update piping in Process questionnaire does not run / + shutdown	normal		V1.0.03ff
	CV	Q3	questionnaire process: when delete the process list is not updated	normal		V1.0.03ff
	BS/CB	Q3	for entering new processes, the user always has to click outside the "Processes data" sheet and back in again. / (probably already solved. -> check ...)
07/11/08	TC Madrid	Q3	Several parameters are asked for that are difficult to obtain in practice (such as return temperature in closed-circuit pipings, ...); Improve the capacity of Einstein to estimate data (such as T_po – process outlet temperature)	normal		?	pending		pending

PanelQ4
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high		V1.0a	12/06/08	SD	pending
24/07/08	BS	Q4	Fuel consumption of boilers -> unit in m3/h or kg/h -> should be written to UnitsFuelConsum	normal	medium	V1.1	24/07/08	HS	pending
16/09/08	HS	Q8		high		V1.0b	24/07/08	HS	pending
10/03/08	CV	FuelConsum	better explanatory text	normal		V1.0a	pending	-	pending
10/05/08	HS	data tables	FUEL_OWN no longer used ...	normal		V1.0a	pending	-	pending
14/07/08	SD	O&M	Define parts of OM costs specified in Q	high		V1.0b	pending	-	pending
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high		V1.0a	12/06/08	SD	pending
	BS/HS	Q4 nomenclature	What is exactly meant be "temperature of feed-up in open circuit"? If the hot water/steam etc. is used in open circuit it is used with its initial temperature, usually, isn't it? / feed-up temperature is usually the COLD water temperature / ok, maybe “boiler feed water temperature” would be more clear?	low	low	V1.0.03
	BS/CB	refrigerant	refrigerant is not stored!	low			pending	-	pending
PanelQ5
	CV	Q5	Distribution: % of recirculation it is not possible to isert 0.99 ...
PanelQ6
	CV	Q6	panelQ6: delete heat exchanger	normal		V1.0.03ff
PanelQ7
	BS/CB	Q7	Renewable energies/Main motivation: / after clicking on the given motives and clicking ok a warning appears: " PanelQ7(OK Button) surface name has to be a unique value"....??	low			pending	-	pending
	BS/CB	biomass	Biomass: are the headings interchanged? / Biomass and main motivation is not stored! only solar roof
PanelQ9 Economics
03/11/08	KK	units in Q9	Economic parameters: (operation/mainenance): EUR/a not EUR!!

Consistency check
12/06/08	HS	connections	connections are not well copied by copying projects / -> links to ID's in original and not in the copy ...	high		V1.0a	19/06/08	HS	pending
11/07/08	CV	Nones to SQL	Writing Nones to SQL gives error (-> implemente check)	high		V1.0b	14/07/08	HS	pending
16/09/08	HS	general algorithm	internal training: -> specifying energy in UPH and pipe parameters is not sufficient for having USH defined, but should be . !!!	normal		V1.00	16/09/08	HS	pending
16/09/08	HS	waste heat	heat recovery for the process ... - 2B linked consistently with the ccheck moduel	normal		V1.00	16/09/08	HS	pending
17/09/08	HS	ccheck and auto-pilot	autopilot passes, although number of required data is > 0	normal		V1.00	17/09/08	HS	pending
27/06/08	CV	HX network and CC	Check consistency between CC calculations and HX network calculations	normal		V1.1	pending	-	-
	CV	Process model	Concept PROCESS: Toutoutflow now cannot be < than PTinflow but if one enter PToutflow< ...it gives an inconsistency. Introduce something to detect / that there is no internal heat exchanger when PTin = PTout then no heat ecxchanger	normal		V1.0.03ff
	CV	links	When user forgets to link processes to pipes into the questionnaires e Warning should be given because otherwise the DATA set / are not consistent	normal		V1.0.03ff
	CV	Energy balances in ccheck and missing data	Ccheck and calculation of missing data: when UPHc and UPHm are both unknown the energy balance (of the estimated values) does not fit with the total UPH	normal		V1.0.03ff
17/10/08	CV	ccheck conflicts	even with a conflict CC writes a congratulation MSG	normal		V1.1	pending	-	-

energyStatistics
02/04/08	HS	window overlap	Switching between windows EA/EM/EH the hide() is not activated.	high		V0.0	02/04/08	TS	ok
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high		V0.1	02/04/08	HS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal		V1.0a	07/04/2008 / 19/06/2008	TS / SD	ok
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high		V0.1	13/04/08	SD	ok
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high		V0.1	30/04/08	SD	ok
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high		V0.1	pending		pending
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high		V0.1	02/04/08	HS	pending
02/04/08	HS	units in display	should be possible to display data in different units; / units should be eliminated from legend	normal		V1.0a	02/04/08	TS	pending
02/04/08	HS	scroll bars in tables	try to avoid	high		V0.1	02/04/08	TS	pending
02/04/08	HS	layout windows	tables should have the same width as figures, ....	high		V0.1	02/04/08	TS	pending
07/04/08	HS	EA windows	number of digits and thousands separtator	normal		V1.0a	07/04/08	TS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal		V1.0a	07/04/08	TS	pending
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal		V1.0a	pending	-	pending
07/04/08	HS	CO2 + nuclear	inlcude CO2 and radioactive waste in the same screen	normal		V1.0a	pending	-	pending
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high		V0.1	13/04/08	SD	pending
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high		V0.1	30/04/08	SD	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high		V0.1	pending		pending

BM Module
2008	BS/CB	product codes	Clearly define product codes within Einstein	normal		V1.1	pending		pending

HR module
23/06/08	HS	importHR	check with Bettina	high		V1.0a	23/06/08	HS/BS	pending
16/09/08	HS	HeatRecOK	Treatment in EINSTEIN of HeatRecOK = “no”: VoutFlow may be > 0, but: / UPHw = 0. Check that this doesn't give problems with HR Module.	high		V1.00	16/09/08	FJ/BS	pending
19/01/09	HS	Internal HR in PE2	Internal heat recovery in PE2 -> consistent treatment ...	high		V1.1	pending		pending
19/01/09	HS	HR and equipes	exhaust gas from equipment not considered in HX network design	high		V1.1	pending		pending
21/10/08	HS	Meat industry case	inconsistencies of heat flows. Check if solved in new version	high		V1.1	pending		pending
21/04/09	HS	HR Test Guide 41	inconsistencies from Ccheck UPHc <> mdot*cp*(Tp – Tin) lead to differences in UPH calculations from core and PE2	medium	medium	V1.1	pending		pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high		V0.0	pending	-	ok
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal		V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low		V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal		V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal		V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal		V1.0a	pending	-	pending
16/09/08	HS	DA's general	counter for default names of equipments (not always 1, 2, 3 ...)	low		V1.1	pending
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal		V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low		V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal		V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal		V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal		V1.0a	pending	-	pending

Connections between equipments
16/10/08	HS	Connections	Data entry in Q4 for waste heat and HT heat source links (a) do not work well and (b) are NOT considered in further calculations !!!	high		V1.01	pending	-	pending
19/01/09	HS	Connect new equipments	New equipments should be connected (e.g. default: connect to ALL pipes ...)	normal		V1.1	pending	-	pending

ST module
27/06/08	HS	sunday	some problem in sunday with projection on tilted surface (returns 0) / for the moment horizontal radiation is used	high		V1.0a	27/06/08	HS	pending
16/09/08	HS	selectST	revise criteria for selection	normal		V1.00	pending
16/09/08	HS	selectST	no available surface should not give problems in quick&dirty design !!	normal		V1.00	pending
16/09/08	HS	selectST	concentrating collectors are not correctly calculated	normal		V1.00	pending
03/11/08	KK	GUI – operating temperature info	Solar module: Average operating temperature is sometimes not readable or minus!!
19/10/08	CV	GUI ST	12) quando cambio manualmente il collettore il sistema non attaulizza i risultati, ovvero non avvia il cacolo delle energy performance. se cambio per es. la potenza si ricalcolano automaticemente le grandezze. per avviare il calcolo cambiando il collettore (manualmente) cosa devo fare? non c'entra nulla il design ass. Immagino.	normal

heatPump
07/04/08	HS	Lists	panel peta si lista equipos (HP's) es vacía ...	normal		V0.0	07/04/08	SD	pending
07/04/08	HS	panel	Pre-assignment in choice; lower-right data as read-only (Static text) ?	normal		V0.0	07/04/08	TS	pending
13/04/08	HS	Module-DeleteEq	DB.commit to be activated ???	high		V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	selected rows should appear in dark	high		V0.0	13/04/08	TS	ok
13/04/08	HS	panelHP	after deleting an equipment, the rows continue appearing in blue. Should be white again	high		V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	editing an equipment by mouse-double click (Q4 – panel appears), the values are not changed after leaving Q4.	high		V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	calculateCascade to be activated after adding/deleting/changing equipment	high		V0.0	pending		pending
13/04/08	HS	moduleHP	Well-working of design-assistant has to be checked	high		V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	function deleteEquipment for erasing space from addEquipmentDummy	high		V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	default buttons should be fully operative	high		V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	adaptation of graphics to specifications	high		V0.0	13/04/08	SD	pending
16/05/08	SD	diverse	check bug-list from 16/05/08 (in HP update from Stoyan)	high		V0.0	pending		pending
19/01/09	HS	HP DA	In some cases (Guide 41 ?) very big heat pumps are designed -> check design assistant ...	normal		V1.0	pending		pending

BB module
16/09/08	HS	boiler	From internal training (EINSTEIN container washing): / Module BB: although the system has a hot water boiler, the DA suggests a steam boiler. selected power is always 800 kW, / although the required power is from 250 - 350 kW (with and without HP)	normal		V1.00	pending		pending
27/10/08	SD	required efficiency	I tried the new BB module with the same case - Meat industry and now the selection results in 2 boilers: 5000 kW(condensing and 4000 kW (steam). In this sence we have improvement. But changing the config parameters (maintaining the first boiler and trying to achieve selection of smaller second boiler) I didn't succeed - the choice was allways the same. Even if I put required efficiency =0.95 the selection was steam boiler 4000 kW with efficiency 0.91. When I reduced the minimum boiler capacity to 100kW - no selection was produced - I send the log. / Can you please explain what means redundancy in the configuration?	normal			pending		pending
18/10/08	CV	manual add of boiler (equipment)	quando inserisci un boiler manual dal DB però ti sbagli e prima di selezionarlo clicki Ok nella finestra supplementare viene aggiunto un boiler nella heat cascade di cui non è specificato il tipo ma non c'è nessun warning. aggiungere messaggio.	normal			pending		pending
19/10/08	CV	boiler dimensioning	systematic testing necessary. Auto-design seems not to react on “redundancy yes/no” and on change of min. operating hours	normal			pending		pending
19/10/08	CV	manual add of boiler (equipment)	se si aggiungono dei nuovi boilers nel questionario non viene trascritto il load factor perchè...perchè non vengono trascritte le ore e i giorni di funzionamento. se queste vengono aggiunte manualmente il LF resta sempre 0	normal			pending		pending

TCA Module
31/10/08	EF	diverse	I'm looking around the tool and I have some questions to ask you about the TCA module. / -1st: MIRR is a number without measurement unit isn't it? In the diagram It is measured in Euro. / -2nd: I think IRR -and MIRR- is a monotonous ascending function of time but in some projects happens the opposite(see WashingSolareTCA.bmp).Could you please explain me the exact meaning of MIRR? / -3rd: looking at the 'Meat industry detailed' project attaced: the 'estim solare' alternative has a HX network and a solar system and has a negative MIRR of -9,68% when the natural gas cost is supposed to be 0,0€/kWh. If I change the fuel cost in 0.12€/kWh the MIRR become -100% and this is quite difficult to explain to me since this alternative consume less gas than the present state (4621MWh vs 9567MWh). / -last: The payback period is indicated even for alternatives with a negative MIRR and NPV and is fixed equal to Time frame for economic analysis - 1.	normal			pending		pending

CS module
16/09/08	HS	CS	Some alternatives sometimes “lose information” and do not appear in the CS statistics. Probably due to StatusEnergy = 0 ???? / -> check WHEN this happens and why ...	normal		V1.00	pending		pending
31/10/08	BS	CS Diagrams: / investment	The CS / diagrammes were discussed a lot in our trainings - the investment e.g. / looks like a staple diagramm, but is not - this was confusing for the / poeple (just to give a small example what we mean).

buildings
02/05/08	HS	Building table	decide wether buildings depend on ANo or ar common to all Anos	normal		V1.0a	02/05/08	HS	pending

Report
13/10/08	HS	Report	Non-ASCII Characters are not well written to OO.	solved		V1.00		HS	solved
31/10/08	BS	report functionality	- Report - We had complains about the pdf button (I know you said it / works), but also more general about the headings/clear structure of the / report and the results displayed in the report - some graphs are still / wrong (pinch graph e.g.) - how can we improve this / or just give the / statement "not working" everywhere where things are not working totally / correct.
19/01/09	HS	report uncomplete	some sheets in the report are not yet linked to the tool / -> BM module (prod01 etc.)	high	medium	?	pending		pending
20/01/09	KK	translations of report	some text does not correctly appear in non-english versions	high	low	?	-	HS	solved
20/01/09	KK	graphics in report	legend of graphics is not translatable	medium	low	?	pending		pending
06/02/09	HS	BCR	Benefit-cost-ratio is translated by cost-benefit ratio in most languages / -> can be misinterpreted as the inverse figure ????	low	low	?	pending		pending

INSTALLER
12/05/08	SD	MySQL passwd	Installer has problems if MySQL is installed already with password	high		V1.0a	pending		pending
09/02/09	Jan Grift	Installer	Erroneous call to sqltest.sql in Installer.	medium	low	V1.0.04	pending		pending

GUIDE
20/10/08	CV	Example 4.3	Some errors in Guide reported

## Ideas
EINSTEIN Tool: List of to do's and ideas to be incorporated in the future

Entry date	Bug advise/idea from	Topic	Description	Priority	Effort	To be changed until version	Notification date	Responsible	Status
GUI General
07/11/08	TC Madrid	Help menu	A help menu is missing (interactive help on the active panel / item)	normal	high	V2.0	pending
31/10/08	BS	GUI – buttons that are not working	block the links/buttons/panels that are not working - we really had / this feedback during the course, We really have enough nicely working / links/buttons, so we do not need the keep the ones that are not working / at all - It seems that users always want to try out each click, and get / upset if something is not working
20/01/09	HS	separation GUI – modules	Structural clean-up: clear separation of GUI, calculation modules and database access / although initially planned as such, in the present state there is several technical functionality within the GUI (checks, etc.). This should be shifted to calculation modules, and GUI should be for display / activation of function calls only	normal	medium	?

E-Questionnaire
21/11/07	CV	Quick assessment	concerning the "one page-simplified -summary questionnaire" that we mentioned on skype last time, I was wondering if this same simplified interface can be also used later on for the (quick) self-assessment module to be used by distance. / Of course I am not able now to see how the self-assessment is going to be mplemented and if it will be based on the same amount of info required for the core tool...It is just a "small window" to be taken open if when implementing the questionnaire and developing the tool in order to save time later on.	normal		V1.0	pending	-	pending
06/03/08		graphical window-layout	Graphical layout into the design of the windows	normal		V1.0a	18/04/08	TS	pending
17/07/08	BS/CB	OK Button	in each subwindow: it is sometime not obvious that it is necessary to confirm the data by ok	normal		V1.1	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: solution proposed = a separate sheet (graphic) for building the connections	normal		V1.1	pending		pending
17/07/08	BS/CB	Fields not needed	Make disappear fields not needed for certain equipment ...	high		V1.1	pending		pending
	BS/CB	Q5 Distribution	Distribution pipe: one cannot define it freely. one before has to go to the distribution questionnaire? this is not very quick	normal		V1.1
25/08/08	BS/CB	reference for enthalpies	Reference for enthalpy values should be clearly specified	normal		V1.1	pending		pending
	BS/CB	OK Button	Avoid errors leaving panels without pressing the OK button ... ask for confirmation: do you really want to leave w/o saving ?	low		V1.1	pending		pending
	BS/CB	Tool-tips	comments should stay longer, is this possible?	low		V1.1	pending		pending
19/01/09	HS	Blocking of Q	Blocking of Q after consistency checking is annoying. Maybe better allowing for read-only access !!!	normal		V1.1	pending		pending
15/11/08	TC Sabadell	Q General	For the pages of the tool's questionnaire where the information is entered in different tabs (e.g. processes, equipment, distribution) and where e.g. the process name is selected in the first tab, but the rest of information for this process is entered in the next tabs – in order to avoid confusion it would be useful to exist a field where the selected process to be shown while you are in the second, third tab... This field could be similar to the field of the active project or interaction mode, so that the user can know in each moment for which process is introducing data.	normal		V1.1	pending		pending
20/11/08	TC Slovenia	display classes	decimal point – decimal comma	low		V1.1	pending		pending

Panel Q1 – general data
	BS/CB	NACE code – list update	general information: after entering NACE code branch - NACE Code subbranch dorp down list is empty, after clicking ok, it appears	low		V1.1	pending		pending
Panel Q2 fuels
20/11/08	TC Slovenia	electricity consumption	Electricity consumption – table is not understandable!	low		V1.1	pending		pending
Panel Q3 – processes
25/08/08	BS/CB	time schedules	hours of operation = Nbatch * Hbatch. Redundancy in data entering. / Should be avoided ... ???	normal		V1.1	pending		pending
	BS/CB	detailed time schedules	variable start-up time (not always 20 %); systematic or random shift between processes; ...	high		V1.1	pending		pending
	BS/CB	process model	Process description: / ?Volume of the process medium within the equipment or storage: e.g. volume of a liquid in a bottle for cleaning? what is meant by this? / We thought here we have to enter the storage or vessel volume for start up heating? / prposal: e.g. volume of washing water that has to be heated before starting a bottle washing machine	normal		V1.1	pending		pending
03/11/08	KK	process Q	6) Visual separation of processdescription general and powerriquerements in operation!	normal		V1.1	pending		pending
03/11/08	KK	process Q	Process data entry: / A graph where you see the standard process. Then you fill in temperatures, flows in the fields along this graph; / It is necessary to provide help for introducing the data for process definition – a graphic of the generic process model with legend to help relating the temperatures with their physical place in the process would be helpful.	high	high	V1.1	pending		pending
2008	CB, BS, HS	multiple process streams	introduction of multiple process streams in / out	high	medium	?	pending		pending

Panel Q4 – equipments
	BS/CB	low temp. heat source	generation of heat and cold: / last page: "low temperature heat source" not very clear what should be entered, low temperature heat source that is used for / boiler feedwater preheating? / maybe definition of low and high temperature in the yellow eyplaination boxes	normal		V1.1	pending		pending
	BS/CB	hide unnecessary fields	in general, many question only are relevant for certain euqipment - can we make only those visible who are relevant currently?	normal		V1.1	pending		pending
	BS/CB	boiler nominal power – input or output ???	Nominal power (Nennleistung?) is not already output, this is the power that is on the label of the boiler isn’t it? I fear it would be confusing for the participants if nominal power would already include the efficiency and it is defined as “nominal power”. At least in austria for sure….	normal		V1.1	pending		pending
Panel Q5 – Distribution
03/11/08	KK	distribution losses in piping	typical losses per meter distribution line should be given (not only as a whole)
Panel Q6 – HX
	BS/CB	LMTD in HX	can logarithmic mean temperature be calculated by the tool?	normal		V1.1	pending		pending
	BS/CB	enthalpy conv.	can the tool calculate specific enthalpy inlet/outlet for the heat source?	normal		V1.1	pending		pending

Panel Q8 Buildings
15/11/08	TC Sabadell	Buildings	The processing of building data is important to be further developed.	high		V1.1	pending		pending

Paper Questionnaire

DB Editor
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	normal		V1.0	19/06/08	TS	pending

Report
12/10/08	HS	panelReport	Speed-up of report generation. Write by blocks instead of cell by cell	normal		V1.1	pending		pending
12/10/08	HS	panelReport	It should be possible to enter all manual inputs required via the GUI. No manual retouch of the Spreadsheet. Optional: automatic pdf generation	low		V1.1	pending		pending
12/10/08	HS	panelReport	Excel – Version of automatic report	low		V2.0	pending		pending

SQL
	HS	Clean-up	systematic elimination (+ checking) of duplicated columns in C-Tables / Renaming of tables / Duplicate variables: ElSales,ElGenera (qelectricity) vs. ElectricityGen,ElectricitySales (cgeneraldata) => ???	low		V2.0	pending		pending
07/11/08	training	import databases	support for importing databases from Excel / spreadsheets	normal		V1.1	pending		pending
10/01/09	CB	database abstraction layer	development of database abstraction layer in between SQL and modules	normal	high	?	pending		pending
19/01/09	HS	project data base	example project data base based on EINSTEIN audits	normal	medium	?	pending		pending
20/01/09	HS	Multi-user access	Multi-user access on same database + individual user databases / Installation of a collective COMPANY database on a local network server; access of several users (e.g. auditors of the same company to the same database; control of privileges / permits). Optional: remote access to central database via internet. / Parallel use of central and local databases (e.g. one user has simultaneously acces to his/her own private data, and to data on a central server	high	medium	?	pending		pending

structural things
21/01/09	HS	Speed-up	Speed-up of calculation times: / - intermediate storage of some arrays / - test if conversion of some functions to C brings speed	high	medium	?	pending		pending

consistency Check
27/06/08	CV	Storage in pipes	Consider storage losses in storage tanks	low		V2.0	pending	-	-
	CV	processes in series	Intelligent ccheck: It should be intersting when two processes are in series that it can etimate the flows etc... taking into account this contraints	low		V1.1
	BS/CB / training	Ccheck info	better info of consistency check: identify source of errors / Improvement of the interface is necessary, especially in reporting the errors in data found with the Consistency Check and Estimate modules – conflicts and estimated data. In this sense some suggestions have been made: / - in case of conflict, in order to help the user tracking the errors in data, it was proposed to change the cell's colour in red for the parameters that should be revised (potentially responsible for conflict) / - in case of estimated data from the tool, similarly, highlight these data in different colour.	high		V2.0
	BS/CB	storage Ccheck	consistency check result is not storeed	low

benchmark module
	BS/CB	Unit operations	List of unit operations; translation ?	low		V1.1

energyStatistics
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal		V1.1	pending	-	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high		V1.0a	pending		pending
03/11/08	KK	list of supply and demand	List at the end needed for all heat and cold supplies - conritbution to demand - not only graphical, but clear list / I think a table where you see: Input/Demand/Difference would be very helpful!!	normal		V1.1	pending	-	pending
15/11/08	TC Sabadell	seasonal demands and hourly profiles	It is important to make operational the monthly and hourly energy statistics.	normal		V1.1	pending	-	pending

Alternative Proposals
17/09/08	HS	PanelA	Alternative name + description should be editable somewhere	normal		V1.1	pending		pending
19/01/09	HS	PanelA	Texto en tabla -> ajustar a tamaño celdas ... / Cambiar Figura en Bar-chart: 2 barras por linea, una para energia, otra para euros (o – si es difícil con dos escalas diferentes, hacer dos figuras ...) / Primera fila debería ser sin número ==> corresponde al estado actual en la industria (ANo = 0)	low		V1.1	pending		pending

Heat Recovery
18/07/08	HS	WHEE	Allow direct connections from WHEE to equipe / process ??? / heat reovery: / the 2nd page (WHEE) adresses only waste heat, the first one real heat exchangers...is this clear for the user to put everything under "heat recovery"?	normal		V1.1	pending		pending
19/01/09	HS	waste heat	Up to now only waste heat streams from processes are considered in PE2 calculations. Waste heat from boilers are displayed, but not included in HX network. / Waste heat from pipes should also be included. / Sinks can be not only process cold streams, but also boilers (air or feed-water preheating) and pipes (preheating of return ...) / Consistent treatment of internal heat recovery in processes within PE2	high		V1.1	pending		pending

HC
19/01/09	HS	HC Panel	Texto en tabla -> ajustar a tamaño celdas ... / Desplegable en “add equipment” con todas las tecnologías.	low		V1.1	pending		pending
19/01/09	HS	cooling	Adaptation of overall concept (cooling as negative heat flows ?, or double accountancy separate: cooling / heating). Adaptation of all relevant modules and corresponding GUI (processes, pipes, supply, hx, energy calculations) / Development of a basic chiller module / Adaptation of PE2 ?	high		V1.1	pending		pending

HP
19/01/09	HS	low temp. heat source	heat pump now takes the aggregate low temp heat supply. As a result, corresponding HX should be created that take this heat ???	normal		V1.1	pending		pending

Solar thermal
16/09/08	CV	roof surface	quick and dirty study should be possible without having a roof surface specified	normal		V1.00	pending	HS	pending
19/01/09	HS	ST and BB	Se ST e BB sono combinati in una alternativa il boilre dovrebbe essere dimensionato sulla potenza picco della domanda orginale (o a velle del process optimization) non su quella residuale a valle del ST. / al momento redundancy può essere superato il problema dal punto di vista pratico ma la info che viene visualizzata come help al dimensionamento è quella residuale (SOLO).	normal		V1.1	pending		pending

Biomass
31/10/08	BS	biomass database	- For renewable energy: It would be great to have at least a few biomass / boilers in the boiler module to show that next to solar thermal we take / into account another source of renewable energy. How could we proceed / best?	normal		V1.1	pending		pending

CHP
19/01/09	HS	CHP	Improvement of CHP module as one of the key technologies: reasonable consideration of all relevant technologies. Basic data base.	high	medium	V1.1	pending		pending

Energy Module
19/01/09	HS	Efficiency	Problem real and nominal COP of equipments / In some equipments COP (HCGTEfficiency) may be depending on operation conditions (e.g. heat pumps, ...). / In these cases HCGTEfficiency from Q4 is used as an INPUT	low		V1.1	pending		pending

TCA
19/01/09	HS	Auto-run	TCA functions should operate automatically as far as possible.	low		V1.1	pending		pending

Electricity for non-thermal uses
15/11/08	TC Sabadell	electricity non-thermal	Further integration of modules for optimization of the electrical consumption for non-thermal use on the platform of Einstein would be desirable.	low	high	V1.1	pending		pending

Report
31/10/08	BS	report	People (in Austrian TC) wanted a shorter report master	low		V1.1	pending		pending

INSTALLER
14/07/08	HS	General	Improve and simplify installer	high		V1.0b	14/07/08	TS	pending
19/01/09	HS	python	Install python in locations different from C:\python25	low		V1.1	pending		pending
19/11/08	TC Slovenia	OpenOffice	Link to openoffice.org	low		V1.1	pending		pending
19/01/09	HS	OpenOffice	Installers for windows, linux and mcintosh	medium	?	V1.1	pending		pending

Self-learning and DB Update
21/11/07	CV	Self-learning of tool	Do you think that it would be useful and to feasible to foresee an authomatic update of the databases / and a statistics module where results of an audit campaign can be stored and compared, summarised etc., by industry sector, country etc.? / Or this module/task should be something completely stand-alone? / We should produce an evaluation report of the audit campaign...	low		V1.1	pending	-	pending

User Manual
2008	BS/CB	OM	clear definition of O&M Categories	low		V1.1	pending	-	pending
19/01/09	HS	installation instructions	1045 error -> clear description; / NET has to be installed (windows computers)	low		V1.1	pending	-	pending

Developer manual
	HS	GUI	definition of GUI functions and standards ...	low		V1.1	pending	-	pending

Guide and training materials
20/01/09	HS	process catalogue	catalogue of typical processes and their representation in Einstein (optionally as default process type database ?)	low	medium	V1.1	pending	-	pending