## ToDos
EINSTEIN Tool: List of to do's and ideas to be incorporated in the future

Entry date	Bug advise/idea from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
Scroll-up menu
03/03/08		DB edit option	Names of DB should be adapted to specifications		V0.0	03/03/08	HH	ok
07/04/08	HS	view alternatives	Alternatives – view should be activated; -> to be revised	high	V0.1	30/04/08	TS	pending
21/04/08	HS	project open/new	Menu bar should lead to PanelQ0	high	V0.0	21/04/08	TS	ok

Tree
06/03/08		SEC	SEC by product / unit operation should adapt to the products / unit operations specified in the given industry	high	V1.0a	pending		pending

GUI – general
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high	V0.1	13/04/08	TS	pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	normal	V1.0a	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high	V0.0	18/04/08	SD	ok
18/04/08	TS	UTF-8 recommended	Windows usa algo parecido a / ISO-8859-1 (llamado también Latin-1). Esta codificación basta para los / idiomas 'occidentales' como castellano, catalán, alemán, francés, / inglés. Pero los idiomas eslavos usan otras (ISO-8859-2, etc.) y si esta / herramienta se quiere usar a nivel de toda Europa, sería mejor pasarse a / UTF-8. El problema radica en que necesitas tener un editor de texto que lo / acepte. / De momento, como sólo estamos usando texto inglés, no habría que hacer / nada especial, excepto recrear la base de datos pasándola a UTF-8 y usando / una versión de Python que acepte UTF-8 también. Creo que siempre hay dos / versiones de Python, una sólo para inglés y Latin-1 y otra / internacionalizada para UTF-8.	low	V1.0	pending		pending

E-Questionnaire
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	normal	V1.0a	pending	-	pending
12/06/08	HS	Q1...Q9	Reasonable limits for value entries ...	high	V1.0a	12/06/08	SD	pending
12/06/08	HS	Q1	Link choices for NACE and product codes	high	V1.0a	12/06/08	SD	pending
12/06/08	HS	Q1	Link text entry branch / sub-branch with nace-codes	normal	V1.0	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: while no defintive solution: improve the comments in the tool tips	high	V1.0	pending		pending
17/07/08	BS/CB	Fields not needed	Make disappear fields not needed for certain equipment ...	high	V1.0	pending		pending
PanelQ2
12/06/08	HS	Q2	Layout	high	V1.0a	11/06/08	TS	pending
PanelQ3
12/06/08	HS	Q3	Reasonable limits; define missing units	high	V1.0a	12/06/08	SD	ok
16/06/08	HS	Q3	Layout; numctrls = None; activate unit conversion	high	V1.0a	16/06/08	TS	pending
PanelQ4ff
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high	V1.0a	12/06/08	SD	pending
PanelQ7
14/06/08	HS	Q7	adapt to new solar module requirements	high	V1.0a	24/06/08	SD/HS	pending

DB Editor
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	normal	V1.0	19/06/08	TS	pending

Self-learning and DB Update
21/11/07	CV	Self-learning of tool	Do you think that it would be useful and to feasible to foresee an authomatic update of the databases / and a statistics module where results of an audit campaign can be stored and compared, summarised etc., by industry sector, country etc.? / Or this module/task should be something completely stand-alone? / We should produce an evaluation report of the audit campaign...	low	V1.1	pending	-	pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high	V0.0	pending	-	ok
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal	V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal	V1.0a	pending	-	pending

energyStatistics
02/04/08	HS	window overlap	Switching between windows EA/EM/EH the hide() is not activated.	high	V0.0	02/04/08	TS	ok
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high	V0.1	02/04/08	HS	pending
02/04/08	HS	units in display	should be possible to display data in different units; / units should be eliminated from legend	normal	V1.0a	02/04/08	TS	pending
02/04/08	HS	scroll bars in tables	try to avoid	high	V0.1	02/04/08	TS	pending
02/04/08	HS	layout windows	tables should have the same width as figures, ....	high	V0.1	02/04/08	TS	pending
07/04/08	HS	EA windows	number of digits and thousands separtator	normal	V1.0a	07/04/08	TS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal	V1.0a	07/04/08	TS	pending
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal	V1.0a	pending	-	pending
07/04/08	HS	CO2 + nuclear	inlcude CO2 and radioactive waste in the same screen	normal	V1.0a	pending	-	pending
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high	V0.1	13/04/08	SD	pending
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high	V0.1	30/04/08	SD	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V0.1	pending		pending

Consistency Check
27/06/08	CV	Storage in pipes	Consider storage losses in storage tanks	low	V2.0	pending	-	-
27/06/08	CV	HX network and CC	Check consistency between CC calculations and HX network calculations	normal	V1.1	pending	-	-

SQL
10/03/08	TS	Capital letters in VarNames	DB is referred to in lowercase letters: in windows works, but linux not !!! check if now it's ok	normal	V0.0	pending	-	pending
07/04/08	HS	Benchmark DB	Include Benchmark DB in SQL	high	V0.0	07/04/08	SD	ok
18/04/08	SD	queries	queries with [0] at the end give error in empty lists / subsitute by query of list and then assignment of index	normal	V1.0a	18/04/08	all	pending

Questionnaire
10/03/08	CV	FuelConsum	better explanatory text	normal	V1.0a	pending	-	pending
10/05/08	HS	data tables	FUEL_OWN no longer used ...	normal	V1.0a	pending	-	pending
14/07/08	SD	O&M	Define parts of OM costs specified in Q	high	V1.0b	pending	-	pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high	V0.0	pending	-	ok
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal	V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal	V1.0a	pending	-	pending

heatPump
07/04/08	HS	Lists	panel peta si lista equipos (HP's) es vacía ...	normal	V0.0	07/04/08	SD	pending
07/04/08	HS	panel	Pre-assignment in choice; lower-right data as read-only (Static text) ?	normal	V0.0	07/04/08	TS	pending
13/04/08	HS	Module-DeleteEq	DB.commit to be activated ???	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	selected rows should appear in dark	high	V0.0	13/04/08	TS	ok
13/04/08	HS	panelHP	after deleting an equipment, the rows continue appearing in blue. Should be white again	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	editing an equipment by mouse-double click (Q4 – panel appears), the values are not changed after leaving Q4.	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	calculateCascade to be activated after adding/deleting/changing equipment	high	V0.0	pending		pending
13/04/08	HS	moduleHP	Well-working of design-assistant has to be checked	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	function deleteEquipment for erasing space from addEquipmentDummy	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	default buttons should be fully operative	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	adaptation of graphics to specifications	high	V0.0	13/04/08	SD	pending
16/05/08	SD	diverse	check bug-list from 16/05/08 (in HP update from Stoyan)	high	V0.0	pending		pending

INSTALLER
14/07/08	HS	General	Improve w. respect to V1.00a	high	V1.0b	14/07/08	TS	pending

## BuggyBugs
EINSTEIN Tool: List of buggy bugs

Entry date	To do from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
Scroll-up menu
03/03/08		DB edit option	Names of DB should be adapted to specifications		V0.0	03/03/08	HH	ok
07/04/08	HS	view alternatives	Alternatives – view should be activated; -> to be revised	high	V0.1	30/04/08	TS	pending
21/04/08	HS	project open/new	Menu bar should lead to PanelQ0	high	V0.0	21/04/08	TS	ok
14/07/08	HS	General	Display of alternative / project ... does not update if new alternatives / are created -> vinculate with SetActiveAlternative/Project	high	V1.0b	pending

Tree
06/03/08		SEC	SEC by product / unit operation should adapt to the products / unit operations specified in the given industry	high	V1.0a	pending		pending
23/06/08	HS	General	Eliminate tree-items not used	high	V1.0b	pending

GUI – general
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high	V1.0a	13/04/08	TS	pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	normal	V1.0a	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high	V0.0	18/04/08	SD	ok
18/04/08	TS	UTF-8 recommended	Windows usa algo parecido a / ISO-8859-1 (llamado también Latin-1). Esta codificación basta para los / idiomas 'occidentales' como castellano, catalán, alemán, francés, / inglés. Pero los idiomas eslavos usan otras (ISO-8859-2, etc.) y si esta / herramienta se quiere usar a nivel de toda Europa, sería mejor pasarse a / UTF-8. El problema radica en que necesitas tener un editor de texto que lo / acepte. / De momento, como sólo estamos usando texto inglés, no habría que hacer / nada especial, excepto recrear la base de datos pasándola a UTF-8 y usando / una versión de Python que acepte UTF-8 también. Creo que siempre hay dos / versiones de Python, una sólo para inglés y Latin-1 y otra / internacionalizada para UTF-8.	normal	V1.0b	pending		pending

Graphics
26/06/08	HS	refresh	Problem with refresh of graphics. Tom has some idea -> to be implemented	high	V1.0b	26/06/08	TS/HS	pending

DB Editor
03/03/08		Exit button	No exit button is foreseen	high	V1.0a	pending	-	pending
25/02/08		Pulldown menu in DB Benchmark	Up to now data bases that are linked with each other have to be entered by the ID-value. No pull-down menu is foreseen. This should be changed later on	high	V1.0b	28/06/08	TS	pending
02/04/08		diferentes Dbs	possibility to edit different equipment DB's: heat pump, boiler, / additional DB's that will come in the future (CHP, chillers, solar / thermal, ...) [por ahora abre la tabla UHeatPump, la cual es la / tabla equivocada]	high	V1.0a	02/04/08	TS	pending
02/04/08		button OK/Cancel		high	V1.0a	02/04/08	TS	pending
02/04/08		select by double clicking		high	V1.0a	02/04/08	TS	pending
13/04/08	HS	DB Editor	preselected list of equipment should be possible	high	V1.0a	13/04/2008 / again: / 28/06/2008	SD / SD	ok
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	high	V1.0b	19/06/08	TS	pending
29/06/08	HS	DB Content	Nulls or other corrupt content in DB's may give problems / -> security feature should be foreseen ... / (example: HP Module with None in HPHeatCap	high	V1.0a	pending

File I/O (export/import project)
23/06/08	HS	import/export	links to be copied	high	V1.0a	23/06/08	TS	pending

SQL
10/03/08	TS	Capital letters in VarNames	DB is referred to in lowercase letters: in windows works, but linux not !!! check if now it's ok	normal	V0.0	pending	-	pending
18/04/08	SD	queries	queries with [0] at the end give error in empty lists / subsitute by query of list and then assignment of index	normal	V1.0a	18/04/08	all	controlled
14/07/08	HS	backup	ERROR MySQL binary folder not known	normal	V1.0b	14/07/08	TS	pending

Paper Questionnaire

E-Questionnaire
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	high	V1.0b	pending	-	pending
25/04/08	HS	Q4	Delete in Q4 doesn't work. / Equipe type – is not passed correctly to addHP, ...	high	V0.1	25/04/08	HS	pending
12/06/08	HS	Q1...Q9	Reasonable limits for value entries ...	high	V1.0a	12/06/08	SD	pending
23/06/08	HS	Q1...Q9	Automatic translation from volume-flow to mass-flow	normal	V1.1	pending
23/06/08	HS	Q1...Q9	height of numCtrl entry fields -> adjust to unit-selector	high	V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	Rounding errors in numCtrls	high	V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	NumCtrls = None	high	V1.0a	June 08	SD	pending
PanelQ1
19/06/08	HS	Q1	Entering from PanelQ0 by “open project”: error messages appear trying to open Q1	high	V1.0a	19/06/08	TS	pending
PanelQ2
12/06/08	HS	Q2	Layout	high	V1.0a	11/06/08	TS	pending
PanelQ3
12/06/08	HS	Q3	Reasonable limits; define missing units	high	V1.0a	12/06/08	SD	ok
16/06/08	HS	Q3	Layout; numctrls = None; activate unit conversion	high	V1.0a	16/06/08	TS	pending
23/06/08	HS	Q1...Q9	with of description field	high	V1.0a	June 08	SD	pending
PanelQ4
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high	V1.0a	12/06/08	SD	pending
24/07/08	BS	Q4	Fuel consumption of boilers -> unit in m3/h or kg/h -> should be written to UnitsFuelConsum	high	V1.0b	24/07/08	HS	pending

Consistency check
12/06/08	HS	connections	connections are not well copied by copying projects / -> links to ID's in original and not in the copy ...	high	V1.0a	19/06/08	HS	pending
11/07/08	CV	Nones to SQL	Writing Nones to SQL gives error (-> implemente check)	high	V1.0b	14/07/08	HS	pending

energyStatistics
02/04/08	HS	window overlap	Switching between windows EA/EM/EH the hide() is not activated.	high	V0.0	02/04/08	TS	ok
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high	V0.1	02/04/08	HS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal	V1.0a	07/04/2008 / 19/06/2008	TS / SD	ok
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high	V0.1	13/04/08	SD	ok
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high	V0.1	30/04/08	SD	ok
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V0.1	pending		pending

HR module
23/06/08	HS	imporHR	check with Bettina	high	V1.0a	23/06/08	HS/BS	pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high	V0.0	pending	-	ok
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal	V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal	V1.0a	pending	-	pending

ST module
27/06/08	HS	sunday	some problem in sunday with projection on tilted surface (returns 0) / for the moment horizontal radiation is used	high	V1.0a	27/06/08	HS	pending

heatPump
07/04/08	HS	Lists	panel peta si lista equipos (HP's) es vacía ...	normal	V0.0	07/04/08	SD	pending
07/04/08	HS	panel	Pre-assignment in choice; lower-right data as read-only (Static text) ?	normal	V0.0	07/04/08	TS	pending
13/04/08	HS	Module-DeleteEq	DB.commit to be activated ???	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	selected rows should appear in dark	high	V0.0	13/04/08	TS	ok
13/04/08	HS	panelHP	after deleting an equipment, the rows continue appearing in blue. Should be white again	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	editing an equipment by mouse-double click (Q4 – panel appears), the values are not changed after leaving Q4.	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	calculateCascade to be activated after adding/deleting/changing equipment	high	V0.0	pending		pending
13/04/08	HS	moduleHP	Well-working of design-assistant has to be checked	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	function deleteEquipment for erasing space from addEquipmentDummy	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	default buttons should be fully operative	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	adaptation of graphics to specifications	high	V0.0	13/04/08	SD	pending
16/05/08	SD	diverse	check bug-list from 16/05/08 (in HP update from Stoyan)	high	V0.0	pending		pending

buildings
02/05/08	HS	Building table	decide wether buildings depend on ANo or ar common to all Anos	normal	V1.0a	02/05/08	HS	pending

INSTALLER
12/05/08	SD	MySQL passwd	Installer has problems if MySQL is installed already with password	high	V1.0a	pending		pending

## Ideas
EINSTEIN Tool: List of to do's and ideas to be incorporated in the future

Entry date	Bug advise/idea from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
E-Questionnaire
21/11/07	CV	Quick assessment	concerning the "one page-simplified -summary questionnaire" that we mentioned on skype last time, I was wondering if this same simplified interface can be also used later on for the (quick) self-assessment module to be used by distance. / Of course I am not able now to see how the self-assessment is going to be mplemented and if it will be based on the same amount of info required for the core tool...It is just a "small window" to be taken open if when implementing the questionnaire and developing the tool in order to save time later on.	normal	V1.0	pending	-	pending
06/03/08		graphical window-layout	Graphical layout into the design of the windows	normal	V1.0a	18/04/08	TS	pending
17/07/08	BS/CB	OK Button	in each subwindow: it is sometime not obvious that it is necessary to confirm the data by ok	normal	V1.1	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: solution proposed = a separate sheet (graphic) for building the connections	normal	V1.1	pending		pending

Paper Questionnaire

SQL

energyStatistics
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal	V1.1	pending	-	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V1.0a	pending		pending

heat reocvery
18/07/08	HS	WHEE	Allow direct connections from WHEE to equipe / process ???	normal	V1.1	pending		pending