## Versions
EINSTEIN Tool: Planing of versions

V1.0	15/10/08	Base version for training courses / Should be 90 % operative
V1.01	30/11/08	Base version for EINSTEIN audit campaign / Correction of most serious bugs detected
V1.1	Mid 2009	End of EINSTEIN project
V2.0	???	In the future when everything is better ...

## BuggyBugs
EINSTEIN Tool: List of buggy bugs

Entry date	To do from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
Scroll-up menu
03/03/08		DB edit option	Names of DB should be adapted to specifications		V0.0	03/03/08	HH	ok
07/04/08	HS	view alternatives	Alternatives – view should be activated; -> to be revised	high	V0.1	30/04/08	TS	pending
21/04/08	HS	project open/new	Menu bar should lead to PanelQ0	high	V0.0	21/04/08	TS	ok
14/07/08	HS	General	Display of alternative / project ... does not update if new alternatives / are created -> vinculate with SetActiveAlternative/Project	high	V1.0b	pending	HS	fixed

Tree
06/03/08		SEC	SEC by product / unit operation should adapt to the products / unit operations specified in the given industry	high	V1.0a	pending		pending
23/06/08	HS	General	Eliminate tree-items not used	high	V1.0b	pending

GUI – general
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high	V1.0a	13/04/08	TS	pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	normal	V1.0a	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high	V0.0	18/04/08	SD	ok
07/04/08	HS	Timing instantiation and updates	problem in energy statistics; ... distinguish between init and update / check update of panels after caclulation, etc. / proposal for solution in EA1. Check with Tom and apply to rest of Eas	high	V0.1	13/04/08	TS	pending
18/04/08	TS	UTF-8 recommended	Windows usa algo parecido a / ISO-8859-1 (llamado también Latin-1). Esta codificación basta para los / idiomas 'occidentales' como castellano, catalán, alemán, francés, / inglés. Pero los idiomas eslavos usan otras (ISO-8859-2, etc.) y si esta / herramienta se quiere usar a nivel de toda Europa, sería mejor pasarse a / UTF-8. El problema radica en que necesitas tener un editor de texto que lo / acepte. / De momento, como sólo estamos usando texto inglés, no habría que hacer / nada especial, excepto recrear la base de datos pasándola a UTF-8 y usando / una versión de Python que acepte UTF-8 también. Creo que siempre hay dos / versiones de Python, una sólo para inglés y Latin-1 y otra / internacionalizada para UTF-8.	high	V1.00	pending		pending
17/04/08	HS	strange characters	strange characters entered via text-boxes give problems (such as 's, or ó,ò,ê,...). -> unicode use ???	high	V1.00	17/04/08	TS	pending
18/04/08	SD	Q+C tables	copying projects the link between Q and C is lost / to be solved by joining Q and C Tables	high	V0.0	18/04/08	SD	ok
16/09/08	HS	Displayclasses	Unit Fraction 100% converts to 100, not to 1.0	high	V1.00	16/09/08	TS
23/09/08	HS	IntEntry	PanelQ4 (year of manufacturing, number of equipes -> does not store / display). Temporarily substituted by float entry with decimals = 0	normal	V1.1	pending
23/09/08	HS	displayclasses	min/max value should be related to internal Value, not to display value	normal	V1.1	pending
25/09/08	HS	auditor db	at present no way to enter auditor contact information ...	normal	V1.1	pending

Graphics
26/06/08	HS	refresh	Problem with refresh of graphics. Tom has some idea -> to be implemented	high	V1.01	26/06/08	TS/HS	pending

DB Editor
03/03/08		Exit button	No exit button is foreseen	high	V1.0a	pending	-	pending
25/02/08		Pulldown menu in DB Benchmark	Up to now data bases that are linked with each other have to be entered by the ID-value. No pull-down menu is foreseen. This should be changed later on	high	V1.01	28/06/08	TS	pending
02/04/08		diferentes Dbs	possibility to edit different equipment DB's: heat pump, boiler, / additional DB's that will come in the future (CHP, chillers, solar / thermal, ...) [por ahora abre la tabla UHeatPump, la cual es la / tabla equivocada]	high	V1.0a	02/04/08	TS	pending
02/04/08		button OK/Cancel		high	V1.0a	02/04/08	TS	pending
02/04/08		select by double clicking		high	V1.0a	02/04/08	TS	pending
13/04/08	HS	DB Editor	preselected list of equipment should be possible	high	V1.0a	13/04/2008 / again: / 28/06/2008	SD / SD	ok
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	high	V1.1	19/06/08	TS	pending
29/06/08	HS	DB Content	Nulls or other corrupt content in DB's may give problems / -> security feature should be foreseen ... / (example: HP Module with None in HPHeatCap	high	V1.0a	pending		generic problem

File I/O (export/import project)
23/06/08	HS	import/export	links to be copied	high	V1.0a	23/06/08	TS	fixed (HS)
16/09/08	HS	import/export	import gives Problems, if previously the project with the highest ID has been deleted ... (conflict of auto-increment in the questionnaire table, and look-up of the import function) / has been provisionnally fixed adding always a dummy project. / Better solution should be found for saving ID'No's	low	V1.1	16/09/08	HS	provisional fix (Sept.08)

SQL
10/03/08	TS	Capital letters in VarNames	DB is referred to in lowercase letters: in windows works, but linux not !!! check if now it's ok	low	V1.1	pending	-	pending
18/04/08	SD	queries	queries with [0] at the end give error in empty lists / subsitute by query of list and then assignment of index	normal	V1.0a	18/04/08	all	controlled
14/07/08	HS	backup	ERROR MySQL binary folder not known	normal	V1.0b	14/07/08	TS	fixed
16/10/08	HS	Database	Several Bugs in SQL tables detected: text declared as “DOUBLE” etc. / -> revise everything, especially the early definitions (first updates)	low	V1.1	pending	-	pending

Paper Questionnaire

E-Questionnaire
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	high	V1.0b	pending	-	pending
25/04/08	HS	Q4	Delete in Q4 doesn't work. / Equipe type – is not passed correctly to addHP, ...	high	V0.1	25/04/08	HS	pending
12/06/08	HS	Q1...Q9	Reasonable limits for value entries ...	high	V1.01	12/06/08	SD	pending
23/06/08	HS	Q1...Q9	Automatic translation from volume-flow to mass-flow	high	V1.00	pending
23/06/08	HS	Q1...Q9	height of numCtrl entry fields -> adjust to unit-selector	high	V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	Rounding errors in numCtrls	high	V1.0a	June 08	SD	pending
23/06/08	HS	Q1...Q9	NumCtrls = None	high	V1.0a	June 08	SD	pending
10/03/08	CV	unit conversion mass flow / volume flow	In some cases both types of data may be allowed -> automatic detection ?	high	V1.00	pending	-	pending
12/06/08	HS	Q1	Link choices for NACE and product codes	high	V1.0a	12/06/08	SD	pending
12/06/08	HS	Q1	Link text entry branch / sub-branch with nace-codes	normal	V1.0	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: while no defintive solution: improve the comments in the tool tips	normal	V1.01	pending		pending

PanelQ1
19/06/08	HS	Q1	Entering from PanelQ0 by “open project”: error messages appear trying to open Q1	high	V1.0a	19/06/08	TS	pending
PanelQ2
12/06/08	HS	Q2	Layout	high	V1.0a	11/06/08	TS	pending
PanelQ3
12/06/08	HS	Q3	Reasonable limits; define missing units	high	V1.0a	12/06/08	SD	ok
16/06/08	HS	Q3	Layout; numctrls = None; activate unit conversion	high	V1.0a	16/06/08	TS	pending
23/06/08	HS	Q1...Q9	with of description field	normal	V1.01	June 08	SD	pending
PanelQ4
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high	V1.0a	12/06/08	SD	pending
24/07/08	BS	Q4	Fuel consumption of boilers -> unit in m3/h or kg/h -> should be written to UnitsFuelConsum	high	V1.00	24/07/08	HS	pending
16/09/08	HS	Q8		high	V1.0b	24/07/08	HS	pending
10/03/08	CV	FuelConsum	better explanatory text	normal	V1.0a	pending	-	pending
10/05/08	HS	data tables	FUEL_OWN no longer used ...	normal	V1.0a	pending	-	pending
14/07/08	SD	O&M	Define parts of OM costs specified in Q	high	V1.0b	pending	-	pending
12/06/08	HS	Q4ff	Reasonable limits; define missing units; choices-functionality; revise layout	high	V1.0a	12/06/08	SD	pending

Consistency check
12/06/08	HS	connections	connections are not well copied by copying projects / -> links to ID's in original and not in the copy ...	high	V1.0a	19/06/08	HS	pending
11/07/08	CV	Nones to SQL	Writing Nones to SQL gives error (-> implemente check)	high	V1.0b	14/07/08	HS	pending
16/09/08	HS	general algorithm	internal training: -> specifying energy in UPH and pipe parameters is not sufficient for having USH defined, but should be . !!!	normal	V1.00	16/09/08	HS	pending
16/09/08	HS	waste heat	heat recovery for the process ... - 2B linked consistently with the ccheck moduel	normal	V1.00	16/09/08	HS	pending
17/09/08	HS	ccheck and auto-pilot	autopilot passes, although number of required data is > 0	normal	V1.00	17/09/08	HS	pending
27/06/08	CV	HX network and CC	Check consistency between CC calculations and HX network calculations	normal	V1.1	pending	-	-

energyStatistics
02/04/08	HS	window overlap	Switching between windows EA/EM/EH the hide() is not activated.	high	V0.0	02/04/08	TS	ok
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high	V0.1	02/04/08	HS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal	V1.0a	07/04/2008 / 19/06/2008	TS / SD	ok
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high	V0.1	13/04/08	SD	ok
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high	V0.1	30/04/08	SD	ok
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V0.1	pending		pending
02/04/08	HS	monthly data	number of columns and number of data in graph not identical. Seems that totals are shown ???	high	V0.1	02/04/08	HS	pending
02/04/08	HS	units in display	should be possible to display data in different units; / units should be eliminated from legend	normal	V1.0a	02/04/08	TS	pending
02/04/08	HS	scroll bars in tables	try to avoid	high	V0.1	02/04/08	TS	pending
02/04/08	HS	layout windows	tables should have the same width as figures, ....	high	V0.1	02/04/08	TS	pending
07/04/08	HS	EA windows	number of digits and thousands separtator	normal	V1.0a	07/04/08	TS	pending
07/04/08	HS	EA windows	primary energy consumption / final energy consumption changed	normal	V1.0a	07/04/08	TS	pending
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal	V1.0a	pending	-	pending
07/04/08	HS	CO2 + nuclear	inlcude CO2 and radioactive waste in the same screen	normal	V1.0a	pending	-	pending
13/04/08	HS	panelEA	check of actualisation in panelEA1. Adapt to other EA / EM / EH panels	high	V0.1	13/04/08	SD	pending
30/04/08	HS	modules EA	-> Modules EA have to be completely revised: not only C->Q, but also filtering of tables by Pid and ANo before calculating sums. / Introduce security checks in order to avoid crash if data are None or tables are empty !!!	high	V0.1	30/04/08	SD	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V0.1	pending		pending

HR module
23/06/08	HS	imporHR	check with Bettina	high	V1.0a	23/06/08	HS/BS	pending
16/09/08	HS	HeatRecOK	Treatment in EINSTEIN of HeatRecOK = “no”: VoutFlow may be > 0, but: / UPHw = 0. Check that this doesn't give problems with HR Module.	high	V1.00	16/09/08	FJ/BS	pending

HC Supply
04/03/08		HC design assistant window	Uniform design of window for assisted design	high	V0.0	pending	-	ok
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal	V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal	V1.0a	pending	-	pending
16/09/08	HS	DA's general	counter for default names of equipments (not always 1, 2, 3 ...)	low	V1.1	pending
2007	CV	Q Equipment	How to deal with groups of identical equipments -> define some consistent procedure; What is asked for in the questionnaire -> power / flow rate / etc of one boiler, or of the group ?	normal	V1.0a	pending	-	pending
08/12/07	CV	Fuel switching	en el tool esta prevista la opcion: / - Fuel Switching ?	low	V1.1	pending	-	pending
08/04/08	BS/HS	Exhaust gas	include calculation of waste heat / exhaust gas flow rate in boiler / CHP / ... modules	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in the boiler module for next versions consider also the opportunity/necessity (???) to introduce: / - the type of fluid to be distributed / - the connection to the pipes number... / - the type of boiler (condensing, ...). / Moreover a link to the HR module concerning off gas heta recovery etc has to implement, later on...	normal	V1.0a	pending	-	pending
16/05/08	CV	Boiler – several	in DB as far as I saw: / the year of construction is missing (while in the interface is quoted) / the fuel is also missed. / right? do we need this info, I think...	normal	V1.0a	pending	-	pending

Connections between equipments
16/10/08	HS	Connections	Data entry in Q4 for waste heat and HT heat source links (a) do not work well and (b) are NOT considered in further calculations !!!	high	V1.01	pending	-	pending

ST module
27/06/08	HS	sunday	some problem in sunday with projection on tilted surface (returns 0) / for the moment horizontal radiation is used	high	V1.0a	27/06/08	HS	pending
16/09/08	HS	selectST	revise criteria for selection	normal	V1.00	pending
16/09/08	HS	selectST	no available surface should not give problems in quick&dirty design !!	normal	V1.00	pending
16/09/08	HS	selectST	concentrating collectors are not correctly calculated	normal	V1.00	pending

heatPump
07/04/08	HS	Lists	panel peta si lista equipos (HP's) es vacía ...	normal	V0.0	07/04/08	SD	pending
07/04/08	HS	panel	Pre-assignment in choice; lower-right data as read-only (Static text) ?	normal	V0.0	07/04/08	TS	pending
13/04/08	HS	Module-DeleteEq	DB.commit to be activated ???	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	selected rows should appear in dark	high	V0.0	13/04/08	TS	ok
13/04/08	HS	panelHP	after deleting an equipment, the rows continue appearing in blue. Should be white again	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	editing an equipment by mouse-double click (Q4 – panel appears), the values are not changed after leaving Q4.	high	V0.0	13/04/08	TS	pending
13/04/08	HS	panelHP	calculateCascade to be activated after adding/deleting/changing equipment	high	V0.0	pending		pending
13/04/08	HS	moduleHP	Well-working of design-assistant has to be checked	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	function deleteEquipment for erasing space from addEquipmentDummy	high	V0.0	13/04/08	SD	ok
13/04/08	HS	panelHP	default buttons should be fully operative	high	V0.0	13/04/08	SD	pending
13/04/08	HS	panelHP	adaptation of graphics to specifications	high	V0.0	13/04/08	SD	pending
16/05/08	SD	diverse	check bug-list from 16/05/08 (in HP update from Stoyan)	high	V0.0	pending		pending

BB module
16/09/08	HS	boiler	From internal training (EINSTEIN container washing): / Module BB: although the system has a hot water boiler, the DA suggests a steam boiler. selected power is always 800 kW, / although the required power is from 250 - 350 kW (with and without HP)	normal	V1.00	pending		pending

CS module
16/09/08	HS	CS	Some alternatives sometimes “lose information” and do not appear in the CS statistics. Probably due to StatusEnergy = 0 ???? / -> check WHEN this happens and why ...	normal	V1.00	pending		pending

buildings
02/05/08	HS	Building table	decide wether buildings depend on ANo or ar common to all Anos	normal	V1.0a	02/05/08	HS	pending

Report
13/10/08	HS	Report	Non-ASCII Characters are not well written to OO.	high	V1.00	pending		pending

INSTALLER
12/05/08	SD	MySQL passwd	Installer has problems if MySQL is installed already with password	high	V1.0a	pending		pending

LISTA Joints 2BChecked !!!!

LISTA KLA August 2008 2B Checked
TOOL questionnaire:

general data
branch and sub-branch: not possible to insert a description when click on OK it gives back NONe

energy consumption
panelQ2 electricity consumption: missing conversion MWh/kWh

processes
panelQ3: chane Mass for Volume in daily outflow of process medium (missing liter as U.M. while in daily inflow there is)

Distribution pipe: one cannot define it freely. one before has to go to the distribution questionnaire? this is not
very quick.

process model
Exchange in the process scheme Tpor and Tpo: tpor = PTOutFlowRec while Tpo = PToutFlow

Process questionnaire:
change in panelQ3 and also in list of parameters the folloing definitions:
Inlet temperature of process medium (before internal heat recovery)
Inlet temperature of process medium (after internal heat recovery)
title: Internal and external waste heat recovery for the process
In the box at least the position and move up the inlet temperature

HR
panelQ6: delete heat exchanger

CCheck
see UNITS.py: Mfuel in m3 gives problems !!

Update piping in Process questionnaire does not run
+ shutdown

default SQRR error = 10^-4 in ccheckfuntion (to avoid conflicts)

Concept PROCESS: Toutoutflow now cannot be < than PTinflow but if one enter PToutflow< ...it gives an inconsistency. Introduce something to detect
that there is no internal heat exchanger when PTin = PTout then no heat ecxchanger

questionnaire process: when delete the process list is not updated

UM generation: fuel consum è un flow kg/h or m3/h NOT kg...

When user forgets to link processes to pipes into the questionnaires e Warning should be given because otherwise the DATA set
are not consistent

Distribution: % of recirculation it is not possible to isert 0.99 ...

Intelligent ccheck: It should be intersting when two processes are in series that it can etimate the flows etc... taking into account this contraints

Cchecka and calculation of missing data: when UPHc and UPHm are both unknown the energy balance does not fit with the total UPH

## Ideas
EINSTEIN Tool: List of to do's and ideas to be incorporated in the future

Entry date	Bug advise/idea from	Topic	Description	Priority	To be changed until version	Notification date	Responsible	Status
E-Questionnaire
21/11/07	CV	Quick assessment	concerning the "one page-simplified -summary questionnaire" that we mentioned on skype last time, I was wondering if this same simplified interface can be also used later on for the (quick) self-assessment module to be used by distance. / Of course I am not able now to see how the self-assessment is going to be mplemented and if it will be based on the same amount of info required for the core tool...It is just a "small window" to be taken open if when implementing the questionnaire and developing the tool in order to save time later on.	normal	V1.0	pending	-	pending
06/03/08		graphical window-layout	Graphical layout into the design of the windows	normal	V1.0a	18/04/08	TS	pending
17/07/08	BS/CB	OK Button	in each subwindow: it is sometime not obvious that it is necessary to confirm the data by ok	normal	V1.1	pending		pending
17/07/08	BS/CB	Connections	inputs conercning distribution line (for current supply) and heat exchangers (for waste heat recovery for this process) / are asked for, but the user has not seen the following questionnaire pages ==> HS: solution proposed = a separate sheet (graphic) for building the connections	normal	V1.1	pending		pending
17/07/08	BS/CB	Fields not needed	Make disappear fields not needed for certain equipment ...	high	V1.1	pending		pending

Paper Questionnaire

DB Editor
19/06/08	SD	DB Editor	predefined text for lists (EquipeType, UnitOp, etc.)	normal	V1.0	19/06/08	TS	pending

Report
12/10/08	HS	panelReport	Speed-up of report generation. Write by blocks instead of cell by cell	normal	V1.1	pending		pending
12/10/08	HS	panelReport	It should be possible to enter all manual inputs required via the GUI. No manual retouch of the Spreadsheet. Optional: automatic pdf generation	low	V1.1	pending		pending
12/10/08	HS	panelReport	Excel – Version of automatic report	low	V2.0	pending		pending

SQL

consistency Check
27/06/08	CV	Storage in pipes	Consider storage losses in storage tanks	low	V2.0	pending	-	-

energyStatistics
07/04/08	HS	Heat & Cold	separation of heat flows and cold flows ???	normal	V1.1	pending	-	pending
10/05/08	HS	Estat + CC	Cuando se llama energyStatistics desde ANo = -1 -> mostar ANo 0 o bloquear	high	V1.0a	pending		pending

Alternative Proposals
17/09/08	HS	PanelA	Alternative name + description should be editable somewhere	normal	V1.1	pending		pending

Heat Recovery
18/07/08	HS	WHEE	Allow direct connections from WHEE to equipe / process ???	normal	V1.1	pending		pending

Solar thermal
16/09/08	CV	roof surface	quick and dirty study should be possible without having a roof surface specified	normal	V1.00	pending	HS	pending

INSTALLER
14/07/08	HS	General	Improve w. respect to V1.00a	high	V1.0b	14/07/08	TS	pending

Self-learning and DB Update
21/11/07	CV	Self-learning of tool	Do you think that it would be useful and to feasible to foresee an authomatic update of the databases / and a statistics module where results of an audit campaign can be stored and compared, summarised etc., by industry sector, country etc.? / Or this module/task should be something completely stand-alone? / We should produce an evaluation report of the audit campaign...	low	V1.1	pending	-	pending